## Project Schedule
CS691, Spring 2022 - Project Delivery Schedule
|  |  |  | Jan-Feb, Class Dates |  |  |  |  | March, Class Dates |  |  |  |  | April, Class Dates |  |  |  | May, Class Dates
Week | CS691 Topics | Owner Role | Deliverables | 2022-01-25 | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-01 | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-10
1 | Chapter 1: Introduction | N/A |  | 2022-02-01: LUNAR NEW YEAR, NOCLASSES; 2022-02-15: c; 2022-03-15: SPRING BREAK, NO CLASSES
2 | Chapter 2: Software Processes | Project Manager | Project proposal | bar: 2022-02-08
3 | Chapter 3: Agile Software Development | Project Manager | PID document | bar: 2022-02-15
| Project Management Overview | Product Owner | bar: 2022-02-15
4 | Chapter 4: Requirements Engineering | Project Manager | Project Plan, RACI | bar: 2022-02-22
5 | Aspect-Oriented Requirements Analysis | Lead BA | Requirements types | bar: 2022-03-01
|  | Lead BA | Analysis diagrams | bar: 2022-03-01
6 | Chapter 5: System Modeling | Product Owner | User requirements | bar: 2022-03-08
|  | Lead BA | RCT | bar: 2022-03-08
7 | Workshop 1: Software Requirements | Lead BA | Functional requirements | bar: 2022-03-22
|  | Team | Workshop 1 preparation | 2022-03-22: WS1
8 | Midterm Exam | N/A | Mid-term exam preparation | 2022-03-29: Exam MT
9 | Chapter 6: Architectural Design | DBA | DB model, ER diagrams (2) | bar: 2022-04-05
10 | Chapter 7: Design and Implementation | Lead Developer | Architecture diagrams (2) | bar: 2022-04-12
11 | Chapter 8: Software Testing | Lead Developer | UML design diagrams | bar: 2022-04-19
12 | Chapter 9: Software Evolution | Lead QA | Test documentation | bar: 2022-04-26
| Workshop 2: Testing Documentation | Team | Workshop 2 preparation | 2022-04-26: WS2
13 | Final Exam | N/A | Final exam preparation | 2022-05-03: Exam Fin
14 | Final Project Presentation | All Teams | Project Presentation | 2022-05-10: ProjPres
|  |  | Project Phases: | 2022-01-25: Project Planning; 2022-02-22: Software Requirements; 2022-04-05: Software Design & Coding; 2022-04-26: Testing
|  |  |  | 2022-01-25 | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-01 | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-10
|  |  |  | Zoom |  | T1 | T3 | T5 | T2 | T4 |  | T1 | T1 | T1 | T3 | T5 | T1 | T1 | T1
[6 empty] | T2 | T4 | T1 | T3 | T5 |  | T2 | T2 | T2 | T4 | T1 | T2 | T2 | T2
[12 empty] | T3 | T3 |  |  |  | T3 | T3 | T3
[12 empty] | T4 | T4 |  |  |  | T4 | T4 | T4
[12 empty] | T5 | T5 |  |  |  | T5 | T5 | T5

## Project Grading Policy
Project Presentation Checklist and Grading
Project Phase | NO | Deliverables | Presentation | Role | Max Points
Project Planning | 1 | Project Plan | NO | PM | 5
| 2 | PID document | NO | PM | 5
Requirements Analysis | 3 | BRM Diagram; User Roles | YES | Product Owner | 4
| 4 | Context Diagram; System Interface Table | YES | Lead BA | 4
| 5 | Architecture Diagrams (Logical, Process views) | YES | Lead Dev/DBA | 5
| 6 | Business Requirements | NO | Product Owner | 6
| 7 | RCT (includes func. decomp., suppl. reqs) | YES | Lead BA | 7
| 8 | Use-Case Diagrams (UML) | YES | Lead BA | 4
| 9 | Activity Diagram (UML) | YES | Lead BA | 4
| 10 | Data-flow Diagrams (logical, physical) | YES | Lead BA | 4
| 11 | Functional Requirements (user stories) | YES | Lead BA | 7
High-level Design | 12 | Class Diagrams | NO | Lead Dev | 4
| 13 | Sequence Diagrams | NO | Lead Dev | 4
| 14 | ER Diagrams (conceptual, logical) | YES | DBA | 5
| 15 | Table Specifications (Data Dictionary) | NO | DBA | 3
Implementation | 16 | Source Code sample (part of Demo) + GitHub repository slides (images) | YES | Lead Dev | 4
Testing | 17 | Test Plan document | YES | Lead QA | 5
Project Presentation | 18 | Application Demo, Presentation PowerPoint | YES | All | 20
|  |  |  | TOT: | 100
Grading is based on assessment of each item consistency with the related guidelines (see next tab).

## Document Guidelines
Project Checklist and Guidelines
General Guideline: before you start working on any deliverable, please review examples on Classes Portal. Note, file names for all documents should be enumerated following the below list of deliverables. Examples: 3. BRM_Team 2; 7. RCT_Team 2
Project Phase | NO | Deliverables | Role | Comments
Project Planning | N/A | Business Cases (2) | PM | 1. Conduct a team meeting, identify 2 candidate applications. Agree when the next "progress check point" meeting will be conducted. 2. Split the team into two streams and assign students to work in parallel on each of the two business cases. 3. Review with the team the examples of Business Cases, make sure the team understands the document sections. 4. Use a Business Case template to produce documents. Review the initial drafts with the team. 5. Send the initial drafts to the Instructor for review and feedback no later than Sunday. This will leave the team 1-2 days for improving the recommended application case.
| 1 | Project Plan | PM | 1. Review Project Plan examples, produce a project plan in Excel format. 2. Discuss with the team what will be the project's lifecycle phases and milestones. Include them in the project plan. 3. Each task in the project plan should have a title, task owner (team member's name), start/end dates, progress (%). 4. The list of tasks should include the main deliverables included in the Project Checklist (Grading Policy). The plan should also include milestones (see examples). 5. Identify a few application features to be implemented this semester and complete the project plan for these features (W7 deliverable).
| 2 | PID document | PM | 1. Follow the PID template on Course portal in Classes. 2. Section "Stakeholders" should include all groups shown in the BRM. 3. Section "Project Plan" should explain which development methodology the team will follow, e.g., Agile, the project phases, iterations, and milestones.
| N/A | Application's Home Page | Lead Dev | 1. Review the system's prototypes referenced in the Business Case. 2. Make a "paper" design prototype (in Word, or PowerPoint, etc.), discuss it with the team. 3. Start coding the Home Page. 4. Add later a menu structure based on the functional decomposition (W6 deliverable).
Requirements Analysis | 3 | BRM Diagram | Product Owner | 1. Follow the BRM template from the lecture material (W4, Slide 20). 2. The central part (internal organization structure) includes data flows among the internal groups. Include your system name in the groups that will be using it. 3. The BRM business groups should match the stakeholders in the PID document. 4. If the internal organization structure includes multiple groups, highlight those groups, e.g., mark with an asterisk, that will be direct users of your application. 5. For each of these groups, identify user roles in a separate slide. Structure user roles by "Internal Users" and "External Users", where the External users should be consistent with the Business Case. 6. The diagram should be delivered in a Power Point document with a title on each slide.
| N/A | Weekly Quiz | All Team Members | 1. A project team creates a quiz on the topic of the last lecture. 2. Each team member creates ONE quiz question and sends it to the Project Manager. 3. The Project Manager collects the quiz questions from all team members; the completed quiz is presented in a table with two columns - Student Name, Quiz Question. The document includes a header indicating the Quiz Topic. 4. The Project Manager sends the completed quiz to the Instructor.
| 4 | Context Diagram | Lead BA | 1. The diagram includes your system and external parties - external systems and main user roles. Note, database is NOT an external system, it is part of your application architecture. 2. For all external systems, the diagram shows data flows with labels indicating the type of data being exchanged. All external interfaces are enumerated to be referenced in the second slide. 3. When showing a user in the diagram, use a UML symbol "Actor" to differentiate it from a system. 4. The second slide includes a System Interface Table explaining external dataflows, see the lecture material (W4, Slide 34). The enumeration of data feeds should be consistent on the first and second slides. Note, inputs from the users do not qualify as system interfaces. 5. The diagram should be delivered in a Power Point document with a title on each slide.
| 5 | Architecture Diagrams (2) | Lead Dev/DBA | 1. Produce two architecture diagrams representing two views - logical (Layered pattern) and process (Client-Server Pattern) views. 2. Include diagrams in a Power Point document, each slide should have a title: - architecture type - architecture view - architecture style (i.e. pattern name)
| N/A | List of Customer Needs | Product Owner | 1. Review prototype systems, compile a list of services these systems provide to Customers. 2. Tailor the original list to your system context, group items in the list by some categories. 3. Finalize and prioritize a list of Customer needs (around 15-20 items) in a Word document.
| 6 | Business Requirements | Product Owner | 1. Follow the BRD template on Course portal in Classes to capture user/business requirements. 2. The document section "Business Scope" describes business groups and user roles from the BRM. 3. The document section "Detailed Requirements" should be structured by the groups of business stakeholders (internal and external) you included in the BRM diagram (2nd slide). 4. Include a section "Data Feeds" that explains the interfaces to external systems you showed in the Context Diagram (2nd slide, System Interface Table). 5. Include a section "Non-functional Requirements" that explains some necessary categories of requirements, use as a reference the classification on Slide 10 (lecture W4). 6. All user requirements should have titles and be enumerated for traceability purposes.
| N/A | Functional Decomposition Diagram (FDD), Fishbone Diagram | Lead BA | 1. Identify functional areas of your application; note a functional area is a sizable part of the application functionality that will include multiple features. A common number of functional areas is between 4 and 6. 2. FDD - Enumerate the identified functional areas (modules); assign a team member to each functional area to lead the RCT development. 3. Fishbone - Use the same module enumeration on the Fishbone diagram where you preliminary identify some core features within each functional area. Do not enumerate the functional features in the Fishbone diagram, you will enumerate them in the RCT.
| 7 | RCT (includes functional decomposition, supplementary reqs) | Lead BA | 1. Follow the RCT template on Course portal in Classes. 2. Include in the RCT the application modules you already identified in the FDD. 3. Analyze the business requirements and identify core application features for each module, include feature ID and titles (name core features). Use as an additional source of ideas the prototypes you included in the Business Case. Check the list of core features in the RCT against the Fishbone diagram, make sure you did not missed in the RCT some features from the Fishbone diagram. 4. Core Feature titles begin with a verb indicating the user's goal. 5. Build a Requirements Traceability Matrix to demonstrate complete coverage of the business requirements. 6. Discuss and agree within the team on the list of Crosscuts; then refine their descriptions in the RCT making them specific to your application. 7. When you have produced a stable RCT draft, discuss with the team and highlight a few core features and their respective crosscuts that the team will implement this semester. 7. In the last Tab "Entitlements" list all roles you identified in the BRM document (Slide 2) and map them to the related core features.
| 8 | Use-Case Diagram (UML) | Lead BA | 1. Produce two use case diagrams for two different modules of your application. 2. Each use case diagram shows a group of related user stories (use cases) and their actors that are in the scope of each module. 3. Discuss actors for each user story in the UC diagrams, update the RCT/ET table if needed; the use case diagrams should be consistent with the RCT/ET table; 3. Each use case in the diagrams has an ID and Title as shown in the RCT, use the UML Actor symbol to represent actors. 4. Highlight those few user stories that the team plans to implement this semester. 5. Include UC diagrams in a Power Point document, where each slide has a title. | UML Actor symbol
| 9 | Activity Diagram (UML) | Lead BA | 1. Create a UML activity diagram to show the primary scenario (an end-to-end flow) of using the application functionality. Note, the flow should have a process start and process end symbols. 2. If applicable, use a swim-lane diagram template; structure the lanes by user roles. 3. The diagram should be delivered in a Power Point document with a title on a slide.
| 10 | Data-flow Diagram (logical) | Lead BA | 1. Review in the RCT some features (stories) the team plans to implement this semester, find those stories that include DF-In/DF-Out crosscuts. 2. Select one of them and elaborate in the logical DF diagram how this core feature exchanges data with other stories; mark the data flows using the crosscut symbols DF-In, DF-Out. 3. Each core feature in the diagram should have an ID and Title as in the RCT. 4. Highlight in the diagram the features that the team plans to implement this semester. 5. The diagram should be delivered in a Power Point document with a title and diagram objective on a slide.
| 10 | Data-flow Diagram (physical) | Lead BA | 1. Open a PP document with the Logical DFD. 2. Copy a logical DFD into a second slide and complete the diagram with the database tables supporting each core feature you plan to implement this semester. 3. Produce DFD diagrams for the core features in scope of this semester implementation. 4. Each slide should have a title.
| 11 | Functional Requirements (user stories) | Lead BA | 1. Follow the template and examples on Course portal in Classes to capture User Stories. 2. For each user story, check the Entitlements specification in the RCT first to understand which roles (Actors) should be included in the user story specification. 3. The list of user stories should match the inventory of core features in the RCT (titles and ID). 4. Indicate which user stories you plan to implement this semester. Mark other user stories as "TBD".
High-level Design | 12 | Class Diagram (UML) | Lead Dev | 1. These UML diagrams are produced for every user story the team selected for implementation this semester. 2. Start with the Class diagram, define class attributes, methods and relationships. Crosscheck class attributes with the fields of related tables (in Table specification). 3. A sequence diagram is produced for a given user story; place the story title from the RCT in the Slide title. 4. A sequence diagram begins with an Actor, use the UML Actor symbol to represent the Actor. 5. Start the Sequence diagram by placing objects that implement a user story; verify that classes of these objects exist in the Class diagram. 6. The sequence diagram should show the same methods that you included in the Class diagram for the same classes. 7. Diagrams are delivered in a Power Point document, where each slide has a title, indicating which user story the diagram represents. | UML Actor symbol
| 13 | Sequence Diagram (UML) | Lead Dev
| 14 | ER Diagrams (conceptual, logical) | DBA | 1. Conceptual database diagram includes the related business entities; it is used for discussions with business stakeholders. Compile the initial list of entities by reading business requirements and titles of core features in the RCT. 2. Logical database diagram includes data tables, table fields, and table relationships. For each table we mark fields that are either primary or foreign keys. 3. Both diagrams show relationships between the entities or tables. 4. The scope of the Conceptual diagram represents the functional scope of the entire application. 5. The scope of the Logical diagram represents the scope of the application implementation that the team plans for this semester. 6. Include both diagrams in a Power Point document, where each slide should have a title.
| 15 | Table Specs + Test Data Specs | DBA | 1. Produce Table specifications in Excel, see examples on the Course portal in Classes, reuse the template. 2. The document includes all tables from the logical ERD. 3. For each table, identify a Primary key and Foreign key (as applicable). 4. For each field in the table indicate the field type, and other details (follow the template). 5. Highlight some tables for which you need to populate test data. 6. Create additional tabs, one for each test data table. 7. Create test data specs for each table, at least a dozen of records in each table. 8. Include in the project plan a task - test data population.
Implementation | 16 | Source Code sample (part of Demo) + GitHub repository slides (images) | Lead Dev | Capture the GitHub info in a PP doc (slides): - login info (first slide) and repository structure (other slides) - sample of your source code representing the feature that will be the focus of your project presentation. - slide with a build/deployment procedure
Testing | 17 | Test Plan document | Lead QA | Follow the Test Plan template on Course portal in Classes. - Introduction section - reference related project documentation, e.g., PID, project Plan (for schedule), RCT (for inventory of functional features), etc. - Features to be Tested section - RCT identified core features and crosscuts - this is what you mention in this section and refer to the RCT. Note, the Test Plan should cover all RCT features as in scope to be tested. - Entry/Exit Criteria - all items in the criteria must be measurable. - Resources and Responsibilities - you can refer to the RACI table, or include it in the document and highlight the testing tasks. - Schedule section - it should be concrete, refer to the project Plan where the Testing phase should be sufficiently detailed - dates, tasks, etc.
| N/A | Test design, test cases (in Excel template) | Lead QA | see a document "CS691_W11_Test Specification Guidelines" on the Course portal, Supplementary Materials module.
Project Presentation | 18a | Application Demo | All | 1. For the application Demo... create a recorded demo, e.g. using QuickTime. 2. For the class presentation, the team needs to rehearse the presentation scenario, decide who is presenting which document. Note, every team member should have a part in the final presentation. 3. For the presentation flow, the team identifies one core feature (user story) and presents and discusses the documents related to this core feature.
| 18b | Presentation PowerPoint | All | 1. All documents presented in class should be included in the PowerPoint document. 2. Each slide includes the image of one document; the title of the slide includes the document name and the student's name, who will present this document. 3. This PowerPoint document is included in the set of final project deliverables.

## Weekly Project Schedule
Weekly Delivery Schedule
Note, "Date" indicates the due date for related deliverables!
Project Phase | Week | Date | Deliverables | Owner Role
| 1 | 2022-01-25
|  | 2022-02-01 | LUNAR NEW YEAR, NO CLASSES
Project Planning | 2 | 2022-02-08 | Project Proposals - Business Cases (2) | PM
| 3 | 2022-02-15 | Project Initiation Document (PID), initial draft | PM
| 3 |  | Quiz - Chapter 2: Software Processes | All
| 4 | 2022-02-22 | Project Plan (in Excel) | PM
| 4 |  | RACI Table | PM
| 4 |  | Completed PID | PM
| 4 |  | Start developing Home Page | Lead Dev
| 4 |  | Quiz - Chapter 3: Agile Software Development | All
Requirements Analysis | 5 | 2022-03-01 | BRM Diagram, User Roles | Product Owner
| 5 |  | Context Diagram, System Interface Table | Lead BA
| 5 |  | Team discussion of Requirements Types, include the tasks in Project Plan | PM
| 5 |  | Compile a list of Customer needs | Product Owner
| 5 |  | Quiz - Chapter 4: Requirements Engineering | All
| 5 |  | Updated Project Plan | PM
| 6 | 2022-03-08 | Business Requirements | Product Owner
| 6 |  | Functional Decomposition (assign SME), Fishbone Diagram | Lead BA
| 6 |  | RCT (includes supplementary requirements) | Lead BA
| 6 |  | Home Page menu stucture | Lead Dev
| 6 |  | Quiz - Aspect-Oriented Requirements Analysis | All
| 6 |  | Updated Project Plan | PM
|  | 2022-03-15 | SPRING BREAK, NO CLASSES
| 7 | 2022-03-22 | Select in the RCT a few features to implement this semester, including crosscuts | PM, Product Owner
| 7 |  | UML analysis diagrams (use case, activity diagrams) | Lead BA
| 7 |  | Data-flow Diagram (logical) | Lead BA
| 7 |  | Functional Requirements (user stories) | Lead BA
| 7 |  | Complete Home Page Demo | Lead Dev
| 7 |  | Project Plan: Elaborate the Coding phase with the selected features | PM
| 7 |  | Quiz - Chapter 5: System Modeling | All
| 7 |  | Requirements Workshop (WS1): preparation | All
| 8 | 2022-03-29 | Mid-term Exam
High-level Design | 9 | 2022-04-05 | ER Diagrams (conceptual -> logical) | DBA
| 9 |  | Database Table Specs + Test Data specs | DBA
| 9 |  | Data-flow Diagram (physical) | Lead BA
| 10 | 2022-04-12 | Architecture Diagrams (2) | Lead Dev/DBA
| 10 |  | Quiz - Chapter 6: Architectural Design | All
| 11 |  | Updated Project Plan | PM
| 10 |  | Watch Git tutorial on YouTube; Establish GitHub projects (Demo) | All
Implementation | 11 | 2022-04-19 | Class Diagram (UML) | Lead Dev
| 11 |  | Sequence Diagram (UML) | Lead Dev
|  |  | Populate test data in the database tables | DBA
| 11 |  | Quiz - Chapter 7: Design and Implementation | All
| 11 |  | Updated Project Plan | PM
| 8,9,10,11 |  | Source code in GitHub repository, executable code ready for testing | Lead Dev
Testing | 12 | 2022-04-26 | Test plan document | Lead QA
| 12 |  | Test design, test cases (in Excel template) | Lead QA
| 12 |  | Quiz - Chapter 8: Software Testing | All
| 12 |  | Updated Project Plan | PM
| 12 |  | Testing workshop (WS2) preparation + application Demo (recorded) | All
Final Exam | 13 | 2022-05-03 | Final Exam preparation
Final Project Presentation | 14 | 2022-05-10 | Presentation preparation | All