## Initial Plan
Color Coding |  | Completed |  |  |  | SPRING 2022 SEMESTER
In Progress
[5 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[5 empty] | Date | 2018-01-25 | 2018-02-08 | 2018-02-15 | 2018-02-22 | 2018-03-01 | 2018-03-08 | 2018-03-15 | 2018-03-22 | 2018-03-29 | 2018-04-05 | 2018-04-12 | 2018-04-19 | 2018-04-26 | 2018-05-03 | 2018-05-10
Project Phase | Activity | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals | ALL | 2018-01-25 | 2018-02-07 | 100%
| Confirm Project Team Roles | ALL | 2018-01-25 | 2018-02-07 | 100%
| Develop two business cases | Saurabh Rai | 2018-01-25 | 2018-02-07 | 100%
| Develop Project Initiation Document (PID) | All | 2018-02-08 | 2018-02-14 | 100%
| Produce initial Project Plan, RACI | Saurabh Rai | 2018-02-15 | 2018-02-21 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles | Kunxi Griswold | 2022-02-25 | 2022-02-28 | 100%
| Produce Context Diagram, Define System Interfaces | Ankit Lele | 2022-02-25 | 2022-02-28 | 100%
| Customer Needs | Viktorija Grillo | 2022-02-25 | 2022-02-28 | 100%
| Define Business Requirements | Viktorija Grillo | 2022-03-03 | 2022-03-08 | 100%
| Define Functional Decomposition | Saurabh Rai | 2022-03-03 | 2022-03-08 | 100%
| Produce RCT document | Saurabh Rai | 2022-03-03 | 2022-03-08 | 100%
| Home Page menu stucture | Nihal | 2022-03-03 | 2022-03-08 | 100%
| Agree to System Requirements types | Saurabh Rai | 2022-03-09 | 2022-03-22 | 100%
| Decide which features to implement this semester | Mrudul Ghagor | 2022-03-09 | 2022-03-22 | 100%
| Produce analysis diagrams (UML, DFD) | Kunxi Griswold, Ankit Lele | 2022-03-09 | 2022-03-22 | 100%
| Define functional requirements (User Stories) | Viktorija Grillo | 2022-03-09 | 2022-03-22 | 100%
| Update Project Plan with additional requirements tasks | Saurabh Rai | 2022-03-09 | 2022-03-22 | 100%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design (2 diagrams) | Nihar Sahu, Nihal Suresh | 2022-04-05 | 2022-04-12 | 100%
| Database Design (ERD, Table spec) | Ankit Lele | 2022-04-05 | 2022-04-12 | 100%
| Data-flow Diagram (physical) | Kunxi Grisworld | 2022-04-05 | 2022-04-12 | 100%
| Class Diagram (UML) | Kunxi Grisworld | 2022-04-12 | 2022-04-19 | 100%
| Sequence Diagram (UML) | Mrudul Ghagor | 2022-04-12 | 2022-04-19 | 100%
| System Interface Design |  |  |  | 0%
| User interface design |  |  |  | 0%
MILESTONE 3: DESIGN COMPLETED
Code | Establish code repository in GitHUb | Saurabh Rai |  |  | 100%
| Coding & Implemenation | Nihal, Nihar | 2022-03-03 |  | 80%
| 01.01 Account Authorisation/Authenticatiom | Nihal, Nihar | 2022-03-03 |  | 80%
| Login Page | Nihal, Nihar | 2022-03-03 |  | 80%
| Sign-Up | Nihal, Nihar | 2022-03-03 |  | 80%
| 01.02 Account Summary | Nihal, Nihar | 2022-03-03 |  | 80%
| View profile | Nihal, Nihar | 2022-03-03 |  | 80%
| Modify profile | Nihal, Nihar | 2022-03-03 |  | 80%
| 02.01 Browse Products | Nihal, Nihar | 2022-03-03 |  | 80%
| Search for a products | Nihal, Nihar | 2022-03-03 |  | 80%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Plan testing, produce a Test Plan document | Kunxi Grisworld, Ankit Lele, Mrudul Ghagor, Nihal Suresh | 2022-04-19 | 2018-04-26 | 100%
| Evaluate Features to be Tested |  |  |  | 0%
| Design Test Cases | Kunxi Grisworld, Ankit Lele, Mrudul Ghagor, Nihal Suresh | 2022-04-19 | 2018-04-26 | 100%
| Execute Test Cases |  |  |  | 0%
| Anaylze Test Results |  |  |  | 0%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation | ALL |  |  | 0%